| ESA STUDY – PROGRESS REPORT |  |  |  |  |
| --- | --- | --- | --- | --- |
| ESA Contract No: 4000117034/16/NL/NDe | SUBJECT: SURGE: Simulating the cooling effect of urban greenery based on solar radiation modelling and a new generation of ESA sensors |  |  | INSTITUTE: Pavol Jozef Šafárik University in Košice, Institute of Geography |
| ESA Contract No: 4000117034/16/NL/NDe |  | No. of Volumes: 1 This is Volume No: 1 |  | INSTITUTE’S REFERENCE: SURGE_PR1 |
| ABSTRACT (Executive Summary of the Project): The aim of this feasibility study is to assess the applicability of the Sentinel-2A multispectral satellite imagery for approximating the dynamics of solar radiation transmittance of urban greenery leading to its cooling effects via modelling the spatial distribution of solar radiation in a complex urban environment represented by a 3-D city model. The main technical objective of the project is to define the relationship between a high-resolution 3-D geometry of urban greenery and vegetation metrics in selected periods throughout the year. The study will be used to evaluate the proposed approach in the development of a toolbox enabling urban planners and researchers to mitigate heat risk based on solar radiation modelling and Sentinel-2A multispectral data. |  |  |  |  |
| The work described in this report was done under ESA PECS Contract. Responsibility for the contents resides in the author or organisation that prepared it. |  |  |  |  |
| Names of authors: Michal Gallay, Jaroslav Hofierka |  |  |  |  |
| ESA PECS PROGRAMME MANAGER: Maite Trujillo DIRECTORATE: IPL-ISP |  |  |  |  |

|  | Doc. No. Issue: Revision: Date: | 1. 1. 1. 15 December 2016 |
| --- | --- | --- |

## Simulating the cooling effect of urban greenery based on solar radiation modelling and a new generation of ESA sensors (acronym SURGE)

Progress Report 1

# Introduction

The objective of the progress report is to provide all actors with actual information concerning the status of the project “Simulating the cooling effect of urban greenery based on solar radiation modelling and a new generation of ESA sensors (acronym SURGE)” from 01/06/2016 to 30/11/2016.

The aim of this project: This project will serve as a preparatory study to assess the applicability of the multispectral satellite imagery for approximating the dynamics of solar radiation transmittance of urban greenery to assess the cooling effects of the greenery via modelling the spatial distribution of solar radiation in a complex urban environment represented by a 3-D city model.

The main technical objectives:  The main technical objective of the project is to define the relationship between 3-D geometry of urban greenery and vegetation metrics in selected periods throughout the year. The imagery to be acquired by the new generation of ESA Sentinel 2-A satellite sensors will be used to derive the vegetation metrics and it will be downscaled to higher resolution datasets. The final outcome of this study will be in the proof-of-concept which identifies critical functions and characteristics of the proposed approach. This study can be used in the future to develop a toolbox enabling urban planners and researchers to mitigate heat risk based on solar radiation modelling and Sentinel-2A multispectral data for urban greenery parameterization.

# Highlight Summary

# During the first 6 months we have achieved the following results:

# The central part of the Košice City was identified as a suitable study area.

# Periodical terrestrial laser scanning of urban vegetation was performed on four smaller sites selected within the study area to acquire ground truth representation of vegetation for particular phenological phases in high resolution and high accuracy.

# Airborne laser scanning data, photogrammetric orthoimagery, and vector based    3-D city model was generated for the study area.

# Multispectral data products of the Sentinel 2A and Landsat 8 sensors were downloaded for the study area and their applicability for the projects was analysed.

# The work is progressing normally according to the plan.

# Work Summary Status (during the reporting period)

| Work package | Activities | Responsible Person | Status |
| --- | --- | --- | --- |
| WP1: Study management | - Meetings of the project team | Jaroslav Hofierka | On-going |
| WP2: Data, methods and architecture of the system | - Review of the state-of-the-art on vegetation transmittance (D1) | Michal Gallay | Finished |
|  | - Selection of the study area | Jaroslav Hofierka | Finished |
|  | - Procurement of services (airborne survey Košice) | Michal Gallay | Finished |
|  | - 3-D city model | Michal Gallay | On-going |
|  | - Generation of 3D time series of urban greenery | Ján Kaňuk | On-going |
|  | - Gathering of Sentinel 2A imagery | Michal Gallay | On-going |
|  | - Urban greenery field mapping | Alena Petrvalská | On-going |

# Detailed Progress of Work

## WP1 – Study management

Since the official start of the project in June (over the last 6 months), we had 2 meetings of the project team. The kick-off meeting was held on 2 June 2016 where we reviewed our research plan and specifically activities for the WP2 for the first 6 months period. We selected the study area (central part of the Košice City) and we briefly discussed conditions of the procurement of airborne laser scanning and data processing. The procedure of the public procurement of the service on airborne laser scanning and photogrammetry of the central part of the Košice City was started in June 2016. The Photomap s.r.o company settled in Košice was selected among three competitors for supplying this service and the data were delivered on 30 November 2016. The second meeting of the project team was held on 7 September 2016, when we reviewed works done and we suggested a detailed plan for finalisation of the activities in WP2 in the remaining period. We had several short presentations on the preliminary results, specifically regarding periodical terrestrial laser scanning of the study area as well as vegetation mapping and photographic documentation of urban greenery. Besides this, the project leader had regular meetings with the WP2 leader discussing the ongoing activities as well as various management and financial issues. The SURGE project website was launched for presenting the aims, team, methods, and results of the project for public (Fig. 1).

Fig. 1. Print screen of the SURGE project website for disseminating the results and work progress on the project.

## WP2 – Data, methods and architecture of the system

Provide summary of the work performed. Upcoming TNs

This feasibility study focuses on the Košice City in Eastern Slovakia as an example of urban space typical for moderate climate of Central Europe. The project team is based in this city therefore it is meaningful to establish the study on an area within Košice. Based on thorough discussions of the team, we selected a study area with a feasible size and sufficient diversity of urban greenery which would be suitable for ground-based mapping, airborne survey and large enough for monitoring by Earth observation satellites such as Sentinel 2A and Landsat 8. The area comprises 4 km2 of the central part of the Košice City and it is delineated in Figure 2. Within this area, we have selected four smaller sites representing certain types of urban greenery (park, alleyway, residential greenery). In these four sites, we have been periodically conducting terrestrial laser scanning (TLS) since April 2016 synchronously with Sentinel 2A overpasses (according to weather conditions +/- 1-2 days). We have also considered the frequency of TLS with respect to the progress in vegetation phenology. Summary of the TLS survey is reported in Table 1. Images of the TLS time series can be seen on the project website http://esa-surge.science.upjs.sk/index.php/study-sites.

Figure 2. Location of the Košice City within Europe (left) and the study area within the city (right). The cyan line outlines the area subject to airborne lidar and photogrammetric data collection and the line delineates selected sites for repeated terrestrial laser scanning. The background maps are © Google.

Table 1. Dates of terrestrial laser scanning data collected on four sites in the study area of the Košice City with associated total accuracy of scans registration.

| City park (Mestský park) | Main street (Hlavná ulica) | Moyzesova ulica (street) | Hvozdíkov park |
| --- | --- | --- | --- |
| April (0.032m) | April (0.029m) | April (0.062m) | April (0.045m) |
| June (0.023m) | June (0.018m) | June (0.023m) | June (0.038m) |
| July (0.029m) | July (0.014m) | July (0.023m) | July (0.016m) |
| August (0.023m) | August (0.016m) | August (0.025m) | August (0.019m) |
| September 14 (0.026m) | September 14 (0.015m) | September 14 (0.034m) | September 14 (0.018m) |
| September 23 (0.024m) | September 23 (0.016m) | September 23 (0.042m) | September 23 (0.018m) |
| October 14 (0.023m) | October 14 (0.010m) | October 14 (0.034m) | October 14 (0.017m) |
| October 27 (0.020m) | October 27 (0.010m) | October 27 (0.024m) | October 27 (0.018m) |
| November 8 (0.020m) | November 8 (0.008m) | November 8 (0.026m) | November 8 (0.017m) |
| November 23 (0.024m) | November 23 (0.012m) | November 23 (0.028m) | November 23 (0.020m) |

Custom aerial survey was procured to acquire 3D airborne laser scanning (ALS) data and photogrammetric imagery to map urban greenery over the whole study area (Fig. 2, 3). Also 3-D vector models of buildings (Fig. 4) were supplied within this service. The data will be used to generate a 3-D city model of the study area in the next 6 month period. Furthermore, we have been continuously downloading Landsat 7 ETM+, Landsat 8 OLI/TIRS, Sentinel 2A multispectral data from the data hubs (Table 2-3, Fig. 5). We conducted preliminary analysis and comparison of the satellite imagery with other data sources. The applicability of multispectral satellite imagery for assessing vegetation transmittance was reviewed and a report was generated as the Deliverable 1 titled “Report on the reviewed applicability of multispectral satellite imagery for derivation of vegetation transmittance”. Detailed field survey of vegetation (trees and bushes) was performed to map the species, health condition, size and other parameters of the greenery within the four sites (Fig.6). In the next period, we will conduct such a survey within the whole study area.

Figure 3. Overview of the acquired spatial data for the study area and associated spatial scales. The images show the central part of the Košice City, Slovakia.

Figure 4. 3-D vector model of buildings derived from the ALS data and photogrammetric data coloured by elevation above mean sea level.

Table 2. Suitable Sentinel 2A level 1C products downloaded to date for the study area

| March | April | May | June | July | August | September | October | November |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 28.3.2016 | 7.4.2016 | 7.5.2016 | 6.6.2016 | 6.7.2016 | 5.8.2016 | 4.9.2016 | 14.10.2016 | 23.11.2016 |
|  | 17.4.2016 | 10.5.2016 | 9.6.2016 | 9.7.2016 | 8.8.2016 | 7.9.2016 |  | 23.11.2016 |
|  | 20.4.2016 | 20.5.2016 | 16.6.2016 | 16.7.2016 | 15.8.2016 | 14.9.2016 |  | 26.11.2016 |
|  | 27.4.2016 | 27.5.2016 | 19.6.2016 | 26.7.2016 | 18.8.2016 | 24.9.2016 |  |  |
|  | 30.4.2016 |  | 26.6.2016 | 29.7.2016 | 25.8.2016 | 27.9.2016 |  |  |
|  |  |  | 29.6.2016 |  | 28.8.2016 |  |  |  |

Figure 5. Estimated clear sky percentage of Sentinel 2A level 1C products downloaded for the Košice City study area in 2016.

Table 3. Landsat 8 level 1 products downloaded to date for the study area of the Košice City.

| March | April | May | June | July | August |
| --- | --- | --- | --- | --- | --- |
| 1.3.2016 | 2.4.2016 | 4.5.2016 | 5.6.2016 | 7.7.2016 | 1.8.2016 |
| 10.3.2016 | 11.4.2016 | 13.5.2016 | 16.6.2016 | 16.7.2016 | 8.8.2016 |
| 17.3.2016 | 18.4.2016 | 20.5.2016 | 21.6.2016 | 23.7.2016 |  |
| 26.3.2016 | 27.4.2016 |  | 30.6.2016 |  |  |

Table 4. Example of attributes recorded in mapping trees in the Košice City.

| Id | Date | Lat | Long | Species | Health | Pheno | Cat | Function 1 | Function 2 | Function 3 | Crown diameter (m) | Urbcat 1 | Urbcat2 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 0208 | 20160714 | 48°43,572 | 21°15,057 | Acer negundo | Z | O | 3 | B | C | D | 6 | A | B |
| 0209 | 20160714 | 48°43,562 | 21°15,048 | Tilia cordata | Z | KK | 3 | B | C | D | 5 | A | B |
| 0210 | 20160714 | 48°43,559 | 21°15,046 | Tilia cordata | Z | KK | 3 | B | C | D | 8 | A | B |
| 0211 | 20160714 | 48°43,551 | 21°15,050 | Tilia cordata | Z | KK | 3 | B | C | D | 6 | A | B |
| 0212 | 20160714 | 48°43,545 | 21°15,052 | Tilia cordata | Z | KK | 3 | B | C | D | 10 | A | B |
| 0213 | 20160714 | 48°43,542 | 21°15,047 | Acer saccharum | Z | O | 3 | B | C | D | 9 | A | B |
| 0214 | 20160714 | 48°43,538 | 21°15,049 | Fraxinus ornus | P25 | O | 3 | B | C | D | 7 | A | B |
| 0215 | 20160714 | 48°43,534 | 21°15,052 | Tilia platyphylos | Z | KK | 3 | B | C | D | 13 | A | B |
| 0216 | 20160714 | 48°43,528 | 21°15,053 | Acer platanoides | Z | O | 3 | B | C | D | 15 | A | B |

Figure 6. Point geodatabase as a result of field mapping of urban greenery mapped in the City park (Mestský park) with assigned attributes shown Table 4.

# Problems, Issues and Risk Areas

We can confirm that no major problems occurred during the first 6 months period. We highly appreciate the on time transfer of the advance payment which was almost fully spend on the supply of the airborne lidar and photogrammetry 3D data for the study area. Therefore, we have no other resources to financially support the project although we are able to subsidise the necessary expenditures from internal university resources until the Milestone 1 is reached. For this reason, we would like to suggest earlier payment of a part of the finances for which we will be eligible after providing the Deliverable 2 “Generated 3D city model”. The results achieved within the first 6 months provide evidence that a significant amount of work was done to reach the Milestone 1 and provide the D2.

# Meetings

| Meeting Name | Description/ Purpose | Location | Planned Date | Actual Date | Attendees |
| --- | --- | --- | --- | --- | --- |
| Kick-off meeting | Kick-off meeting of the team | Kosice | 2nd June 2016 | 2nd June 2016 | Pavol Jozef Safarik University |
| Regular team meeting | Presentation of progress and discussion of planning and problems | Kosice | 7th September 2016 | 7th September 2016 | Pavol Jozef Safarik University |
| Progress meeting | Progress meeting | Kosice | June 2017 |  | Pavol Jozef Safarik University |
| Final meeting | Final meeting | Kosice | May 2018 |  | Pavol Jozef Safarik University |

# Deliverables Status

| Deliverable Identifier | Title/ Description | Original Delivery Date | Planned Delivery Date | Associated Milestone | Status |
| --- | --- | --- | --- | --- | --- |
| D1 | Report on the reviewed applicability of multiscpetral satellite imagery for derivation of vegetation transmittance | Nov-2016 | Nov-2016 | Milestone 1 | Finalised |
| D2 | Generated 3-D city model | May-2017 | May-2017 | Milestone 2 | Planned |
| D3 | Midterm report | May-2017 | May-2017 | Milestone 2 | Planned |
| D4 | Report on derivation of satellite based vegetation metrics and downscaling to high-resolution data | Nov-2017 | Nov-2017 | Milestone 3 | Planned |
| D5 | Report on definition of algorithmic structure of the toolbox | Feb-2018 | Feb-2018 |  | Planned |
| D6 | Roadmap report on implementation of the toolbox | May-2018 | May-2018 | Final | Planned |
| TDP | Technical data package (containing all approved technical notes) | May-2018 | May-2018 | Final Review | Planned |
| FPR | Final Project Report | May-2018 | May-2018 | Final Review | Planned |
| ESR | Executive Summary | May-2018 | May-2018 | Final Review | Planned |

# Milestone Payment Plan: Status

| ID | Description | Amount | Contractual date | Actual/ Expected Date | Status |
| --- | --- | --- | --- | --- | --- |
| MP1 | Advance payment: Offset against MS1 | 17500 | Upon signature of the Contract by both Parties | xxx | Paid |
|  | Progress (MS1): Upon successful completion and delivery of D1 & D2 under WP2 and acceptance of all related deliverables | 12500 | June 2017 | June 2017 | Not yet Due |
|  | Progress (MS2): Upon successful completion and delivery of D4 under WP2 and acceptance of all related deliverables | 12450 | December 2017 | December 2017 | Not yet Due |
|  | Final Settlement (MS3): Upon the Agency's acceptance of all deliverables items due under the Contract and the Contractor's fulfilment of all other contractual obligations including submission of the Contract Closure Ducumentation | 7491 | June 2018 | June 2018 | Not yet Due |

# Planning

# Action Item – Status List

NA

# Any other Business

This feasibility study was contracted within the first call of the ESA/PECS projects for Slovakia. Therefore, the Ministry of Education, Science, Research and Sport of theSlovak republic is keen to organize public meetings to promote the interest and capabilities of Slovakia to contribute to the European space research. We were invited to present the aims of the SURGE feasibility study in Bratislava during two events. The first was held at premises of the Ministry on 1 December 2015 where Jaroslav Hofierka presented the key approach of the SURGE project. The second event on 5 May 2016 was held at the Slovak Technical University in Bratislava where Michal Gallay presented a poster on the SURGE project aims and research approach. The main goal of the event was the talk of the Director General of the ESA Johann-Dietrich Wörner to the Slovak research community about the ESA’s vision and future perspective.

# Reasons for slippage and/or

NA